## general
id | subject | description | sprint_id | Points | N° task | Time estimation | Time effective | Acceptance Criteria
1 | Development server setup | Have a server that can be used to run self-hosted versions of services. | 1 | 28 | 3 | 20 |  | service in cas and our application needs to be accessible from the external
2 | Cas setup | Verify CAS is working as intended, include it in self-launch deps: 1(done) | 1 | 17 | 6 | 5 | 5 | all service available in the cas enviroment are up and running(excluded bugzilla and logger)
3 | SonarQube setup | SonarQube setup, to run in our server. Acceptable to find alternative. Every developer also has to install SonarLint. | 1 | 16 | 4 | 5 | 5 | we can test our git repository of the project with sonarqube
4 | Taiga setup | Taiga has to be set-up in order to run self-hosted in our Google Cloud server. It is acceptable to find an alternative; OpenProject works and is fairly easy to setup, but does not allow boards in the free version. | 1 | 29 | 2 | 10 |  | Taiga is up and running on the self hosted gcloud. basic features are supported. Developers understand rudimentary usage notions and promise to use it <_< OPTIONAL: event support, download support, gitlab integration
5 | API self-study | Everyone has to have a basic understanding of how Twitter API v2 + v1 work. | 1 | 1 | 13 | 5 | 3 | If you understand the backend, you're good.
6 | User Last Tweets | As a user, I want to be able to input a username and receive a list of the last few tweets he sent. Was initially included in sprint 1, later removed in grooming and made optional | 1 |  |  | 8 |  | a user can input a twitter username in the main web page of our application and his last tweets are showed
7 | HashTag Last Tweets | As a user, I want to be able to input a HashTag and receive a list of the last few tweets that mentioned it. Was initially included in sprint 1, later removed in grooming and made optional | 1 |  |  | 8 |  | unlikely to be completed, as historical search is not currently supported. either way, i put in a hashtag and a list is updated with the LAST tweets that contained it.
8 | Trending Hashtag | As a user, I want to be able to see a list of the Trending Hashtags. | 1 |  |  | 8 |  | trending hastag are showed on the main web page in a list
9 | Word Cloud to map | As a user, I want to be able to select a term from the wordcloud and see a map of where the collected tweets were sent from. | 1 |  |  | 20 |  | pretty clear from the description: after clicking on a term in the wordcloud, the interface gets updated to show, on the map, only the tweets that contained that word
10 | Mattermost setup | setup mattermost on self hosted gcloud | 1 | 6 | 1 | 4 | 1 | mattermost is reachable by both browser and phone, and running on self hosted gcloud
11 | Starting Geolocated Filtered Stream | As a user, I can input a coordinate box and start collecting tweets coming from that box. | 1 | 20 | 6 | 15 |  | After inputting coordinates, as a user I can receive the tweets that were collected. OK both in bulk and single tweets.
12 | Export | As a user, after I have collected a number of tweets, I am able to download the collection. | 2 | 16 | 4 | 3 | 3 | clicking the export buttons trigger a download events in the browser of the json containing all the collected tweets
13 | Start Building Database | As a developer, I want to have a teeny tiny database of tweets (geolocated, possibly mentioning our hashtag) to: - test stuff out (play with json files, investigate maps in next sprint...) - show that our collecting function is working correctly - build a database for next sprints Database: literally a single or multiple JSON files | 2 | 17 | 3 | 10 | 5 | Somebody somewhere has a database I can gain access to, even if it takes time. It's important it exists, ease of access is secondary
14 | Make features REALTIME | As a user, I'm able to see the counter of the tweets increase, a subset of tweets, and some preview in real time as tweets are collected. Consequently, all features are updated in real time | 2 | 25 | 4 | 10 | 9 | Client-received tweets are updated not in bulk but in small pieces (acceptable either time-frame or every tweet)
15 | Word Cloud from stream | as a user i can view a word cloud with terms used in the tweets in selected stream | 3 | 17 | 8 | 10 | 15 | a word cloud is correctly generated and showed on client screen, updates with new tweets
16 | Map visualization of hashtags | As a user, I want to be able to visualize geolocated tweets from one or more hashtags on a map | 3 | 28 | 13 | 36 | 27 | after the stream is started with an hashtag, as tweets are received a clickable marker is showed on the map. Clicking on the marker shows the full tweet. If too many tweets are made in the same place, just one marker is showed.
17 | Import tweet collection | As a user, I am able to upload a collection of tweets to "analyze" | 3 | 16 | 3 | 10 | 7 | a json previously exported can be imported and tweets are showed in the map
18 | Time tracking for prod metrics | Consider various alternatives to collect time tracking data, in particular https://wakatime.com/integrations and https://www.kimai.org/about/ | 3 | 18 | 3 | 3 | 6 | Time tracking tool approved by POs
19 | Map visualization of users tweets | As a user, I want to be able to visualize geolocated tweets from one or more users on a map | 3 | 21 | 2 | 10 |  | After starting a stream and collecting some tweets, I can push a button (?) and a map opens, showing the locations of the tweets collected. ALTERNATIVELY As tweets are collected, their location is shown on a map, which gets progressively populated.
20 | Photos from stream on map | As a user i can insert an hashtag and see (eventually also download) a list of phots that are insert in the tweets that mention my hashtag. Extra points: place photos corresponding to tweet on map | 3 | 20 | 3 | 30 | 9 | After inputting a hashtag, I can collect some tweets that mention it. Afterwards, I can download all images contained in bulk. Test with: #apple
21 | Notification on threshold | As a user, I want to be able to set up a notification when a certain condition is met, of which the details are left to the implementers, which notifies me by email. | 3 | 15 | 3 | 12 | 8 | FIRST TEST: condition based on amount of tweets: when enough tweets are collected, send out notification by email.
22 | Tweet amount chart by time | As a user, I want to be able to search a hashtag and see the volume of tweets by unit of time in a given period, to judge the impact an event has had. | 4 | 23 | 6 | 25 | 17 | UNLIKELY. a graph shows the volume of tweets received per unit of time. the tweets are the ones that respect the filters
23 | Periodic tweet | As a user, I want twitter-tracker to automatically and periodically tweet one or more of the analysis on a stream I started. | 4 | 30 | 13 | 30 | 40 | A tweet is sent out, FROM MY ACCOUNT, with the information I selected. I can setup the tweet, test the authentication worked, see the changes both in the client and the result in the tweet. Timeframes: a week maximum, for sure. minimum is hours.
24 | Background searches | I want to be able to start a search and close the window, then find it again when i log back in. | 4 | 20 | 7 | 15 | 17 | The browser window can be closed, and there is some identification method that allows me to "log" back in and see the updated search
25 | BIG interface rework | Complicated to add specific requirements: this will be specified once features are completed. | 4 | 31 | 5 | 22 | 21 | Rework the interface completely. Main interactive part will be the map. include common user interface for email/tweet/filters.
26 | Make coordinate interactive | Find a way to make input of coordinate interactive. it can be two movable markers, drawing a square, or selecting from a list of pre-drawn country squares | 4 | 23 | 9 | 17 | 18 | Will have to be defined when a good compromise between doability and effectiveness is found. UPDATE: after drawing a rectangle on the map, i can start a stream which has as constraints the correct coordinates.
27 | Filters on data | As a user, once the data is displayed, i want set more descriptive filters than those used during the stream | 4 | 15 | 7 | 20 | 19 | Once the filters are selected, the number of tweets displayed increases or decreases depending on whether they respect the filters entered. changes are applied to the whole list, so they affect all visualizations.